Academic English Practice App

Agile Development Plan (Revised — Web Application)

Tech Stack: React + Flask + SQLite + OpenAI API

1. Product Goal & Vision

Product Goal: Build a web application that helps incoming university students transition from everyday English to academic English, enabling them to confidently participate in lectures, seminars, and academic discussions before starting their degree.

Target Users: Non-native English speakers at pre-university level, anxious about classroom participation, with limited time (prefer 5–15 min sessions).

2. Technology Stack

| Layer | Technology | Why |
| --- | --- | --- |
| Frontend | React + Vite + Ant Design | Fast dev build, rich component library, large ecosystem |
| Backend | Python Flask | Lightweight, easy AI integration, fast to develop |
| Database | SQLite + SQLAlchemy | Zero config, easy migration to PostgreSQL later |
| AI Service | OpenAI Chat API | Conversation, quiz generation, feedback |
| Voice | Web Speech API (browser native) | Free, no 3rd-party SDK needed |
| Auth | Flask-Login | Simple session auth, minimal code |
| CI/CD | GitHub Actions | Free, auto test on every PR |
| Deploy | Render (free tier) | Auto-deploy on merge to main |

⚠ Browser Compatibility Note: Web Speech API has limited support on Safari. Recommend Chrome for full voice features. Safari users will see a graceful fallback message.

3. Team Structure & Role Rotation

| Sprint | Week | Product Owner | Scrum Master | Developers |
| --- | --- | --- | --- | --- |
| Sprint 1 | Week 3 | Yanbin Xu | Yanshuo Liu | Junfan Zhou, Yupei Yang, Ruoqi Hu, Weike Jin, Chenxi Huang |
| Sprint 2 | Week 4 | Junfan Zhou | Yupei Yang | Yanbin Xu, Yanshuo Liu, Ruoqi Hu, Weike Jin, Chenxi Huang |
| Sprint 3 | Week 5 | Ruoqi Hu | Weike Jin | Yanbin Xu, Yanshuo Liu, Junfan Zhou, Yupei Yang, Chenxi Huang |
| Sprint 4 | Week 6 | Chenxi Huang | Yanbin Xu | Yanshuo Liu, Junfan Zhou, Yupei Yang, Ruoqi Hu, Weike Jin |

Frontend vs Backend Grouping

Each sprint, members naturally split into frontend and backend focus based on their assigned tasks. One member acts as a bridge (handles API integration between front and back). The bridge person is whoever has the lightest individual task load that sprint.

4. GitHub Collaboration Workflow

4.1 Branch Strategy: Feature Branch Model

- main branch: always stable, deployable. Protected by branch rules.

- Feature branches: created from main for each task, e.g. feature/T1.4-daily-words

- Bug fix branches: e.g. fix/word-bank-delete-error

4.2 Pull Request (PR) Rules

- Every task = one branch = one PR. Never commit directly to main.

- PR description must include: what was done, how to test it, any notes for reviewer.

- At least 1 teammate must Code Review and approve before merging.

- CI must pass (green check) before merging is allowed.

- After merging, delete the remote branch to keep the repo clean.

4.3 Daily Git Workflow (Every Developer)

Before starting work: git pull origin main → git checkout -b feature/T1.x-task-name

During work: Commit often with clear messages, e.g. "feat: add daily words API endpoint"

When done: git push origin feature/T1.x-task-name → Open PR on GitHub → Tag reviewer

After review: Merge PR → Delete remote branch → Move Trello card to Done

4.4 API Contract: The Key to Parallel Work

On Day 1 of each sprint, the whole team spends 30–60 minutes defining every API endpoint for that sprint. This goes into docs/api-sprintX.md. Format:

GET  /api/daily-words  → Returns today’s 5–8 words with definitions, examples, audio flag

POST /api/word-bank    → { word_id: int } → 201 Created

...each endpoint with request params and response JSON structure

Why this matters: Frontend developers can build pages using mock data immediately. Backend developers build APIs to match the contract. When both sides finish, integration is seamless because the interface was agreed upon in advance.

5. Project Structure (Monorepo)

academic-english-app/

├─ frontend/                  # React + Vite

│   ├─ src/pages/             # Page components (DailyWords, WordBank, Listening...)

│   ├─ src/components/        # Shared UI components (NavBar, AudioPlayer...)

│   ├─ src/api/               # API request functions (mock-ready)

│   └─ src/assets/            # Images, icons

├─ backend/                   # Flask

│   ├─ app/routes/            # API route handlers

│   ├─ app/models/            # SQLAlchemy models

│   ├─ app/services/          # Business logic, AI calls

│   └─ tests/                 # pytest tests

├─ docs/                      # API contracts, meeting notes, architecture

├─ .github/workflows/         # CI/CD config

├─ .env.example               # Environment variable template

└─ README.md                  # Setup instructions

6. Sprint Plans

Sprint 0 (Week 2): Preparation

| Activity | Tasks | Assignee | Output |
| --- | --- | --- | --- |
| Requirements | Refine user stories, write acceptance criteria | All Team | Updated Backlog |
| Architecture | System design, DB schema draft, API structure, page routing plan | Yanbin Xu, Yanshuo Liu | Architecture Doc |
| Environment Setup | Create GitHub repo, setup React+Vite & Flask projects, write README setup guide, configure .env.example | Junfan Zhou, Yupei Yang | Working repo everyone can clone and run |
| UI/UX Design | Wireframes for all core pages (7 pages: Home, Daily Words, Word Bank, Listening, Speaking, AI Chat, Profile) | Ruoqi Hu, Weike Jin | Figma Prototypes |
| Sprint 1 Planning | Estimate tasks, define Sprint 1 API contracts, assign work | Chenxi Huang | Sprint 1 Plan |

Sprint 1 (Week 3): Vocabulary Module

Sprint Goal: Deliver functional Vocabulary Hub — users can register/login, see daily words, and save to personal word bank.

PO: Yanbin Xu | SM: Yanshuo Liu | Capacity: 7 × 10h = 70h

| ID | Task | Pri | Assignee | Hours | Dep | Collaboration Notes |
| --- | --- | --- | --- | --- | --- | --- |
| T1.0 | Frontend project setup (React+Vite, router, Ant Design, API module with mock) |  | Yanbin Xu | 8 | — | Day 1 start. All frontend tasks depend on this. |
| T1.1 | Database schema design & implementation (SQLAlchemy models) |  | Junfan Zhou | 8 | — | Day 1 start, parallel with T1.0. |
| T1.2 | Backend Flask API framework + route structure |  | Yupei Yang | 8 | T1.1 | Before T1.1 merges: setup Flask skeleton, folder structure, config. After T1.1 merges: connect DB and implement route stubs. |
| T1.3 | User authentication (register/login, Flask-Login sessions) |  | Ruoqi Hu | 6 | T1.2 | While waiting: build login/register frontend pages with mock API. After T1.2 merges: implement auth routes and connect to frontend. |
| T1.4 | Daily Words feature (API + display page + browser TTS) |  | Weike Jin | 8 | T1.0, T1.2 | While waiting for T1.2: build Daily Words page UI using mock data from T1.0. After T1.2: implement backend API + connect frontend. TTS: use browser SpeechSynthesis API (no backend needed). |
| T1.5 | Word Bank feature (add/remove/list/review) |  | Chenxi Huang | 8 | T1.2, T1.3 | While waiting: build Word Bank page UI with mock data. After T1.3 merges: connect to auth + implement backend CRUD routes. |
| T1.6 | CI/CD pipeline (GitHub Actions: lint + test on PR) |  | Yanshuo Liu | 6 | — | Day 1 start, independent. Setup branch protection rules on main. |
| T1.7 | Unit tests for vocabulary APIs |  | Junfan Zhou | 4 | T1.4, T1.5 | Start after T1.4/T1.5 PRs are up. Test daily-words endpoint, word-bank CRUD, auth guards. |
| T1.8 | Integration testing (end-to-end flow) |  | Yupei Yang | 4 | T1.7 | Final day: register → login → see words → save to bank → view bank. File bugs as GitHub Issues with clear reproduction steps. |

Total planned: 60h / 70h capacity (86% utilization) — leaves buffer for unexpected issues.

Sprint 1 Day-by-Day Coordination

| Day | Key Activities | Merge Events |
| --- | --- | --- |
| Mon | Sprint Planning (2h): define sprint goal, review tasks, write API contracts. T1.0, T1.1, T1.6 start immediately (no dependencies). T1.2 starts Flask skeleton. Others: build frontend pages w/ mock data. | API contract doc committed |
| Tue | T1.0 and T1.1 finish and submit PRs. Yupei Yang reviews T1.1 immediately, merges, continues T1.2. |  |
| Wed | T1.2 finishes. T1.3, T1.4, T1.5 fully unblocked. Three devs work in parallel on auth, daily words, word bank. |  |
| Thu | T1.3, T1.4, T1.5 submit PRs. Cross-review. Begin integration: pull all into main, test full flow. |  |
| Fri | T1.7 unit tests + T1.8 integration tests. Bug fixes. Sprint Review + Retrospective. | All tests + fixes merged. Sprint complete. |

Sprint 2 (Week 4): Listening + Speaking Basics

Sprint Goal: Deliver Listening Lab (beginner/intermediate) and Speaking Studio Level 1 (pronunciation practice).

PO: Junfan Zhou | SM: Yupei Yang | Capacity: 70h

| ID | Task | Pri | Assignee | Hours | Dep | Collaboration Notes |
| --- | --- | --- | --- | --- | --- | --- |
| T2.1 | Listening content DB structure + seed data |  | Yanbin Xu | 6 | — | Day 1 start. Prepare audio clips + transcripts + questions. Seed DB with at least 6 clips across 2 difficulty levels. |
| T2.2 | Audio player component (HTML5 <audio> + custom controls) |  | Yanshuo Liu | 6 | — | Day 1 start, independent. Reusable component. Play/pause, speed control, progress bar. |
| T2.3 | Listening comprehension exercise page |  | Ruoqi Hu | 8 | T2.2 | While waiting: build page layout with mock data. After T2.2: integrate audio player component. |
| T2.4 | AI quiz question generation (OpenAI API) |  | Weike Jin | 8 | T2.1 | Backend: send transcript to OpenAI, generate comprehension Qs. Return questions in standard JSON format for T2.3 to consume. |
| T2.5 | Word Quiz feature (spelling, listening formats) |  | Chenxi Huang | 6 | Sprint 1 | Builds on Sprint 1 word bank data. Independent from listening tasks. Can start Day 1. |
| T2.6 | Pronunciation recording (MediaRecorder API + playback) |  | Junfan Zhou | 8 | — | Day 1 start, independent. Browser MediaRecorder API. Record user voice, play back, send to backend for analysis. |
| T2.7 | Speech recognition integration (Web Speech API) |  | Yupei Yang | 8 | T2.6 | Browser SpeechRecognition for real-time transcription. Compare user speech to target sentence for basic scoring. |
| T2.8 | Sentence follow-along practice |  | Yanbin Xu | 4 | T2.7 | Display sentence, user reads aloud, show match result. Lightweight: reuses T2.6 recording + T2.7 recognition. |
| T2.9 | Sprint 1 bug fixes |  | Ruoqi Hu + Yanshuo Liu | 4 | — | 2 people share bug duty. Check GitHub Issues from Sprint 1. Fix in separate branches, PR as usual. |
| T2.10 | Unit + integration testing |  | Yanshuo Liu | 4 | All | Final day: test all listening + speaking flows end-to-end. |

Total planned: 62h / 70h capacity (89% utilization).

Sprint 3 (Week 5): Advanced Speaking + AI Conversation

Sprint Goal: Deliver Speaking Studio Level 2 (structured expression with AI feedback) and AI Conversation with 2 guided scenarios (Office Hours + Seminar Discussion).

PO: Ruoqi Hu | SM: Weike Jin | Capacity: 70h

| ID | Task | Pri | Assignee | Hours | Dep | Collaboration Notes |
| --- | --- | --- | --- | --- | --- | --- |
| T3.1 | Structured speaking with topic cards |  | Yanbin Xu | 8 | — | Day 1 start. Topic card selection UI + 30-60s recording. Reuses recording component from Sprint 2. |
| T3.2 | AI feedback system (fluency, accuracy, logic scoring) |  | Yanshuo Liu | 8 | T3.1 | Backend: send user transcript to OpenAI with scoring prompt. Return structured feedback JSON. While waiting: design prompt + test in playground. |
| T3.3 | Academic expression template library |  | Junfan Zhou | 6 | — | Day 1 start, independent. Database of useful phrases. Phrases like "I would like to build on that point..." |
| T3.4 | AI conversation dialog engine (2 fixed scenarios) |  | Yupei Yang | 10 | — | Day 1 start. Core AI chat backend. System prompts define scenario context + evaluation criteria. |
| T3.5 | Guided scenario frontend + conversation UI |  | Chenxi Huang | 8 | T3.4 | While waiting: build chat UI page (message bubbles, input). After T3.4: connect to backend dialog engine. |
| T3.6 | Voice input/output for AI chat (Web Speech API) |  | Ruoqi Hu | 8 | T3.4 | SpeechRecognition for voice input, SpeechSynthesis for AI replies. While waiting: build voice controls UI and test speech APIs standalone. |
| T3.7 | Post-conversation report generation |  | Weike Jin | 5 | T3.5 | After conversation ends: OpenAI summarizes performance. Display report card with strengths, areas to improve, key phrases used. |
| T3.8 | Sprint 2 bug fixes + integration testing |  | Junfan Zhou + Yanshuo Liu | 6 | All | Shared duty. Junfan: bug fixes (3h). Yanshuo: integration test (3h). |

Total planned: 59h / 70h capacity (84% utilization) — extra buffer for AI integration complexity.

⚠ Individual workload check: Yupei Yang has 10h (at limit). All others ≤ 8h. No one exceeds the 10h/week cap.

Sprint 4 (Week 6): Integration, Polish & Bonus Features

Sprint Goal: Complete system integration, thorough testing, polish, and deliver production-ready product. Bonus features attempted if time allows.

PO: Chenxi Huang | SM: Yanbin Xu | Capacity: 70h

| ID | Task | Pri | Assignee | Hours | Dep | Collaboration Notes |
| --- | --- | --- | --- | --- | --- | --- |
| T4.1 | Progress tracking dashboard |  | Ruoqi Hu | 6 | — | Day 1 start. Shows completed exercises, scores, time spent. Pulls data from all modules (vocab, listening, speaking, AI chat). |
| T4.2 | Academic Culture module (text tips + do/don’t cards) |  | Yupei Yang | 6 | — | Simplified scope: text-based tips cards (no video). Quiz at end using existing quiz component from Sprint 2. |
| T4.3 | Advanced listening (detail capture exercises) |  | Yanshuo Liu | 6 | — | Moved from Sprint 3. Adds Advanced difficulty level. Reuses existing Listening Lab components. |
| T4.4 | Full system integration testing |  | Weike Jin | 8 | All | Test complete user journey across ALL modules. Cross-browser test (Chrome, Firefox, Edge at minimum). |
| T4.5 | User acceptance testing (UAT) |  | Chenxi Huang | 8 | T4.4 | Test with real user scenarios (the "Sarah" story). Check every acceptance criterion in the backlog. |
| T4.6 | Performance + security optimization |  | Yanbin Xu | 6 | — | Page load speed, API response time, input sanitization. HTTPS, CORS config, environment variables for secrets. |
| T4.7 | Bug fixes and refinements |  | Junfan Zhou + Ruoqi Hu + Yanshuo Liu | 10 | T4.4 | 3 people share. Pick bugs from GitHub Issues by severity. Target: zero P1 bugs, all P2 bugs documented. |
| T4.8 | Documentation (user guide + API docs) |  | Junfan Zhou | 4 | — | User guide: how to use the app (with screenshots). API docs: update docs/ folder with final endpoint specs. |
| T4.9 | Final demo preparation + rehearsal |  | All Team | 8 | — | Prepare demo script, seed demo data, rehearse "Sarah" scenario. Assign speaking parts. Run through twice minimum. |
| T4.N1 | Free Talk AI conversation mode |  | Yanshuo Liu | 8 | Sprint 3 | Open topic selection, no fixed scenario. Reuses Sprint 3 dialog engine with different system prompt. |
| T4.N2 | Challenge Mode (difficult scenarios) |  | Junfan Zhou | 6 | Sprint 3 | Disagreement scenarios, rapid follow-up questions. Reuses dialog engine with harder prompts. |
| T4.N3 | Difficulty levels for listening (Beginner/Inter/Advanced labels) |  | Weike Jin | 3 | T4.3 | Add filter/label UI to listening page. Quick win if T4.3 is done early. |

Core tasks total: 62h / 70h capacity. Nice-to-have tasks add up to 17h extra — only attempted if Thursday check-in confirms core is stable.

7. Product Backlog (Ordered by Value)

| # | ID | User Story | Pri | Pts | Sprint Delivery |
| --- | --- | --- | --- | --- | --- |
| 1 | US01 | Daily academic words with definitions, examples, audio | Must | 5 | Sprint 1 |
| 2 | US02 | Save words to personal bank for later review | Must | 3 | Sprint 1 |
| 3 | US03 | Listen to lecture clips with comprehension questions | Should | 8 | Sprint 2 |
| 4 | US04 | AI pronunciation feedback on speaking | Should | 8 | Sprint 2 |
| 5 | US12 | Track progress (dashboard with scores, time) | Must | 5 | Sprint 4 |
| 6 | US05 | Vocabulary quizzes (spelling, listening, fill-in-blank) | Must | 5 | Sprint 2 |
| 7 | US06 | Difficulty levels in listening exercises | Must | 5 | Sprint 4 (T4.3 + T4.N3) |
| 8 | US07 | Structured speaking practice with AI feedback | Should | 8 | Sprint 3 |
| 9 | US08 | AI conversation practice (guided scenarios) | Nice to have | 13 | Sprint 3 |
| 10 | US10 | Academic culture tips and classroom norms | Nice to have | 5 | Sprint 4 (simplified) |
| 11 | US09 | Free conversation mode | Nice to have | 8 | Sprint 4 Nice-to-have |
| 12 | US11 | Challenge mode for difficult situations | Nice to have | 8 | Sprint 4 Nice-to-have |

8. Agile Ceremonies

Daily Standup (15 min — text in WeChat/Discord group)

Each member posts 3 lines every morning:

- What did I complete since last standup?

- What will I work on next?

- Any blockers? (tag the person who can unblock you)

SM updates Trello board and burndown chart after reading standups.

Sprint Planning (2 hours, Day 1)

- PO presents sprint goal

- Whole team writes API contracts for this sprint (30–60 min)

- Team selects backlog items, breaks into tasks

- Individual workload check: no one exceeds 10h

- Commitment made, tasks go on Trello board

Sprint Review (1 hour, Last Day)

Demo working software. PO checks acceptance criteria. Collect feedback.

Sprint Retrospective (1 hour, Last Day)

Three questions: What went well? What didn’t go well? What will we change? Actions tracked and reviewed next sprint.

9. Definition of Done (DoD)

| Criterion | Standard |
| --- | --- |
| Code Complete | All code written, follows conventions, merged to main via PR |
| Code Reviewed | At least 1 team member reviewed and approved the PR |
| CI Passed | GitHub Actions green check — lint + tests pass |
| Unit Tested | ≥80% coverage, all tests pass |
| Integration Tested | Works correctly with other modules |
| UI/UX Verified | Matches Figma design, responsive down to tablet width |
| Browser Tested | Works on Chrome + Firefox (minimum). Safari voice features may degrade gracefully |
| Documentation | Code comments, API docs in docs/ folder updated |
| No Critical Bugs | Zero P1 bugs, P2 bugs documented in GitHub Issues |
| PO Accepted | Meets acceptance criteria, PO signs off |

10. Testing Strategy

| Test Type | When | Responsible | Tools |
| --- | --- | --- | --- |
| Unit Testing | During development | Each developer | pytest (backend), Jest (frontend) |
| Integration Testing | End of each sprint | Assigned tester | pytest + Postman |
| UI Testing | After feature complete | Ruoqi Hu, Weike Jin | Manual + browser DevTools |
| Cross-Browser | Sprint 4 | Weike Jin | Chrome, Firefox, Edge |
| User Acceptance | Sprint 4 | Chenxi Huang | Real user scenarios |
| Performance | Sprint 4 | Yanbin Xu | Lighthouse, browser DevTools |

11. Progress Tracking & Transparency

| Artifact | Location | Updated By | Frequency |
| --- | --- | --- | --- |
| Product Backlog | Trello board | PO | As needed |
| Sprint Backlog | Trello sprint board | SM | Daily |
| Burndown Chart | Trello or spreadsheet | SM | After each standup |
| Task Status | Trello columns (To Do / In Progress / Done) | Each developer | Real-time |
| API Contracts | docs/api-sprintX.md in GitHub | Whole team | Sprint Day 1 |
| Meeting Notes | docs/meetings/ in GitHub | SM | After each ceremony |

12. Risk Management

| Risk | Prob | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| OpenAI API integration issues | Med | High | Prototype in Sprint 0, test prompts early, have fallback (hardcoded responses for demo) | Yupei Yang |
| Web Speech API browser limits | Med | Med | Recommend Chrome. Build graceful fallback message for unsupported browsers | Ruoqi Hu |
| Team member unavailable | Low | Med | Cross-training via PR reviews, pair programming, shared docs | SM |
| Scope creep | Med | High | Strict backlog management, PO gatekeeping, Nice-to-have buffer | PO |
| Underestimated complexity | Med | Med | 10–15% time buffer per sprint, daily standup risk flags | SM |
| Merge conflicts | Med | Low | Small PRs, frequent merges, API contracts reduce overlap | All |

13. Team Member Responsibility Matrix

| Member | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 |
| --- | --- | --- | --- | --- |
| Yanbin Xu | PO, Frontend Setup (8h) | Listening DB (6h), Follow-along (4h) | Structured Speaking (8h) | SM, Security (6h) |
| Yanshuo Liu | SM, CI/CD (6h) | Audio Player (6h), Bug fix (2h), Testing (4h) | AI Feedback (8h), Integration (3h) | Advanced Listening (6h), Bug fix (3h) |
| Junfan Zhou | Database (8h), Unit Tests (4h) | PO idle, Pronunciation (8h) | Expression Library (6h), Bug fix (3h) | Bug fix (4h), Docs (4h) |
| Yupei Yang | Backend API (8h), Integration (4h) | SM, Speech API (8h) | AI Dialog Engine (10h) | Culture Module (6h) |
| Ruoqi Hu | Auth System (6h) | Exercise UI (8h), Bug fix (2h) | PO, Voice I/O (8h) | Dashboard (6h), Bug fix (3h) |
| Weike Jin | Daily Words (8h) | AI Quiz (8h) | SM, Conversation Report (5h) | Integration Test (8h) |
| Chenxi Huang | Word Bank (8h) | Word Quiz (6h) | Guided Scenarios (8h) | PO, UAT (8h) |

⚠ Rule: If any member’s total exceeds 10h during Sprint Planning, tasks must be redistributed before committing.

14. Deliverables Summary

| Sprint | Working Software | Documentation | Agile Artifacts |
| --- | --- | --- | --- |
| 1 | Vocabulary Module (Daily Words + Word Bank + Auth) | DB Schema, API Docs, README | Backlog, Sprint 1 Board, Burndown |
| 2 | + Listening Lab + Speaking L1 + Word Quiz | Test Reports | Sprint 2 Board, Retro Notes |
| 3 | + Speaking L2 + AI Guided Conversation (2 scenarios) | Integration Report | Sprint 3 Board, Feedback Log |
| 4 | Complete App (+ Dashboard, Culture, Advanced Listening, bonus features if time) | User Guide, Final Report | All Boards, Demo Script |

15. Demonstration Checklist

Demo Structure (15 min total):

- Opening (1 min): Product introduction

- Problem Statement (1 min): Why this app matters

- Target Users (1 min): "Meet Sarah, an incoming international student..."

- Live Demo (5–7 min): Walk through Sarah’s journey — login, learn words, listen to lecture, practice speaking, have AI conversation

- Technical Architecture (2 min): React + Flask + OpenAI, key design decisions

- Agile Evidence (2 min): Show backlog, sprint boards, burndown charts, retro improvements

- Testing Evidence (1 min): CI pipeline, test coverage, cross-browser results

- Conclusion (1 min): Value delivered, known limitations, future improvements

— End of Plan —